## Task breakup sheet
Project | CRM ID | Dev Task ID | Description | Task # | Task Description | Task Type | Dependency ID | Parent ID | Team Lead | Allotted To | Effort (Hrs) | Story Points | Value Points | Start Date | End Date
Sharada Mechanical Engineering | 106206 | SI-54486 | Required Provision to Trigger “BOM Master Data Entry Screen” to BOM (Bill of Material) | 1 | fetching entry data from BOM master |  |  | 106206 | Mohammad Tauseef Ahmed | Naveen Kumar | 4 | 3 |  | 2023-05-08 | 2023-05-08
|  |  |  | 2 | posting data into bill of material screen according to output Itemand input Items |  |  | 106206 | Mohammad Tauseef Ahmed | Naveen Kumar | 4 | 3 |  | 2023-05-09 | 2023-05-09
|  |  |  | 3 | checking if transaction asscoiated with BOM |  |  | 106206 | Mohammad Tauseef Ahmed | Naveen Kumar | 2 | 4 |  | 2023-05-09 | 2023-05-09
|  |  |  | 4 | if any transaction then revision creation |  |  | 106206 | Mohammad Tauseef Ahmed | Naveen Kumar | 2 | 4 |  | 2023-05-09 | 2023-05-10
|  |  |  | 5 | updating it in the version field in the bill of material by comma seperated |  |  | 106206 | Mohammad Tauseef Ahmed | Naveen Kumar | 4 | 4 |  | 2023-05-10 | 2023-05-10
|  |  |  | 6 | if no transaction update and deletion reflect into bill of material screen |  |  | 106206 | Mohammad Tauseef Ahmed | Naveen Kumar | 3 | 4 |  | 2023-05-10 | 2023-05-11
|  |  |  | 7 | if any transaction then revision creation and restrict the user to delete BOM in Bill of Material screen |  |  | 106206 | Mohammad Tauseef Ahmed | Naveen Kumar | 3 | 4 |  | 2023-05-11 | 2023-05-11
|  |  |  | 8 | Testing |  |  | 106206 | Mohammad Tauseef Ahmed | Naveen Kumar | 2 | 2 |  | 2023-05-12 | 2023-05-12